## Cover
Quality by Design (QbD) Documentation Tool
Overview
This tool helps study teams capture and communicate decisions about what is critical to quality, as well as how the most important risks will be proactively addressed. It can be used in conjunction with the QbD Implementation Guide and other tools supporting implementation at the trial level (see links below). In many cases, the same person should be responsible for updating and tracking decisions in both tools. Importantly, this tool is not intended as a replacement for a detailed quality management or monitoring plan. Rather, consider using this tool—starting at the draft study concept stage—to capture the most important study design decisions made collaboratively between study designers, clinical operations personnel, and other stakeholders; and then subsequently build detailed monitoring plans based on the decisions captured in this tool. The worksheets in this tool (Plan, Monitor, Reflect) align with the overview diagram below. Also included is a worksheet for capturing basic information about the study (Study Info), and an Appendix that can be modified to change options listed in drop-down menus in certain cells.
Related Trial-Level QbD Implementation Tools
QbD Implementation Guide
CTQ Principles Document
Perspectives for QbD Discussions and Potential Champions
QbD Recommendations
See additional resources in CTTI's QbD Toolkit

## Study Info
STUDY INFORMATION Use this page to capture basic information about the study, adding and removing fields as necessary to support accurate record-keeping. For "Primary Contact Name", we suggest indicating the individual identified as responsible for using this tool.
Study Name or ID:
ClinicalTrials.gov identifier:
Primary Contact Name:
Primary Contact Email:

## Plan
IDENTIFY & PRIORITIZE CTQs, RISKS & MITIGATION STRATEGIES Involve the broad range of stakeholders in protocol development and discussions around study quality. First identify the Critical-to-Quality Factors (CTQs) for the study. Note that the study design will influence the number of CTQs; however, care should be taken to avoid diluting resources and focus with an excessive number. For each CTQ, identify key risks, determine whether each risk will be mitigated or accepted, and describe either plans to mitigate or rationale to accept the risk. There may be multiple risks per CTQ, and multiple mitigation strategies per risk. | [6 empty] | For this sheet only. (Do not roll over to next tab)
Quality Factor (See CTQ Principles Document) | Truly Critical to Quality? (See Decision Tree) | Specific Risk for Study | Accept/Mitigate | Mitigation Strategy or Rationale for Accepting Risk | Mitigation Type | Mitigation Status | Notes
Withdrawal Criteria and Trial Participant Retention | Yes | Study visit may take 4-6 hours to complete | Mitigate Risk | Review all activities and look for opportunities to eliminate procedures and data collection unrelated to the primary questions of interest. | Study Design | Implemented | This example is provided to help illustrate how this worksheet can be used to provide a summary of CTQs, risks, and mitigation strategies. This row can be deleted from the worksheet if desired.
|  |  |  | Conduct mock visit with a potential site to identify particular pain points from a site perspective that merit consideration for streamlining. | Study Design | Implemented
|  |  |  | In-person visits strongly preferred; however, we are evaluating possibilities for televisits and/or mobile nursing, where applicable, as well as patient concierge services. | Study Execution | Under Consideration
|  | Caregiver presence is required for all study visits | Accept Risk | This is a pediatric trial. Based on patient advisory board discussions, the same strategies identified for reducing patient burden will also reduce caregiver burden. Both are important; however, we do not anticipate identifying additional strategies targeted exclusively at caregivers. | NA | NA
Note on F2: Cells in this column will automatically display "NA", for "Not Applicable", when the coresponding entry in column D is "Accept Risk".
Note on G2: Cells in this column will automatically display "NA", for "Not Applicable", when the coresponding entry in column D is "Accept Risk".

## Monitor
Assessment date:
MONITOR CTQs, RISKS, & MITIGATION STRATEGIES THROUGHOUT STUDY CONDUCT Throughout study conduct, regularly assess and evaluate management of risks to CTQs. Document evidence of mitigation strategy working (or not), identify new risks, and consider whether all CTQs are still relevant. Leverage existing risk-based monitoring systems to guide these discussions. Create new copies of this worksheet for each assessment completed. |  |  |  | For this sheet only. (Do not roll over to next tab)
CTQ | Is CTQ still relevant? | Are key risks appropriately controlled? (Provide assessment and rationale; list any important new risks identified) | What changes to protocol or trial oversight are needed to better mitigate key risks? (Describe planned changes and rationale; or enter "none") | Notes
Have new critical-to-quality factors been identified? If so, document them below. |  |  |  | For this sheet only.b)
CTQ | Specific Risk for Study | Mitigation Strategy | Mitigation Status | Notes
Note on A3: This column will pre-populate from the Plan worksheet. Only Quality Factors that are identified as 'truly critical to quality' ("Yes" in column B) will be displayed.

## Reflect
REFLECT AT STUDY CLOSEOUT In study retrospective, consider what worked, what didn't, and what could be improved next time. Were the right risks identified? Did the mitigation strategies work?
1. What worked well? Consider…
What key risks were well-controlled throughout the study?
What mitigation strategies worked particularly well?
What factors led to success with QbD processes?
2. What could be done better next time? Consider…
What important risks were not anticipated?
What mitigation strategies did not work well?
What factors led to challenges or issues with QbD processes?
3. Actions
How can we better identify risks in future studies?
How can we implement better mitigation strategies in future studies?
How else can we improve QbD processes in future studies?

## Appendix
Critical-to-Quality Factors (CTQs) from Principles Document |  | Risk + Mitigation Options | Monitor Options
Topic | Example CTQ Factors | Accept/Mitigate | Anticipated?
Protocol Design | Eligibility Criteria | Accept Risk | Anticipated
| Randomization | Mitigate Risk | Unanticipated
Masking
| Types of Controls | Mitigation Type
| Data Quantity | Study Design
| Endpoints | Study Execution
| Procedures Supporting Study Endpoints and Data Integrity | Both
Investigational Product (IP) Handling and Administration
Feasibility | Study and Site Feasibility | Mitigation Status
| Accrual | Under Consideration
Patient Safety | Informed Consent | Implemented
| Withdrawal Criteria and Trial Participant Retention | Not Implemented
Signal Detection and Safety Reporting
Data Monitoring Committee (DMC)/Stopping Rules
Study Conduct | Training
Data Recording and Reporting
Data Monitoring and Management
Statistical Analysis
Study Reporting | Dissemination of Study Results
Third-Party Engagement | Delegation of Sponsor Responsibilities
Collaborations
Other
Truly Critical to Quality?
Yes
No
Undecided